## ProductBackLog
Project Name: AI Personal Health & Fitness Coach Group Members: Mehmet Kahraman, Kerem Güneş, Utku Sertkaya, İsmail Yiğit Şendur, Onur Açar, Salikh İbragimov
# | Product BackLog
1 | Database planning and optimization for meals, exercises, and user data
2 | Implementation of Scrypt password hashing and AES-256 encryption for user data
3 | Implementation of backup and disaster recovery system
4 | Development of user registration (email & password) and login/logout system
5 | User profile management (name, profile picture, bio editing)
6 | Implementation of premium membership system (advanced AI features, plans)
7 | Integration of in-app purchase functionality
8 | Setup of AI infrastructure and selection of the most suitable AI model based on project objectives
9 | Customization and fine-tuning of the AI model using our custom datasets
10 | Automation of scientific paper analysis to customize the AI model, and integration of RESTful API to connect the AI system with research data
11 | Integration of Hugging Face API for personalized workout plan generation
12 | Development of an AI-based meal plan and exercise plan generation system
13 | Development of exercise plan components including sets, repetitions, intensity, and visual guidance
14 | Design interactive home screen layouts for daily AI-generated meal and workout plans, optimizing readability and user engagement
15 | Development of push notification system (exercise reminders, meal alerts)
16 | Development of leaderboard and ranking algorithm
17 | Creation of challenge system (weekly goals and competitions)
18 | Scientific studies analyses and AI-generated summaries
19 | Integration with Apple Health and Google Fit
20 | Development of admin panel for user and content management

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | Database planning and optimization | In Progress | High | 2027-06-08 | 2027-06-14 | 6 | Ensure compatibility with future AI-based meal/exercise plan integration
Developer, Product Owner | Data Encryption | Ready to Start | High | 2027-06-14 | 2027-06-16 | 2 | Document encryption and hashing procedures for team reference.
Developer, Product Owner | Backup and disaster recovery system | Ready to Start | High | 2027-06-15 | 2027-06-17 | 2 | Plan automated backup and restore procedures
10
BACKLOG
As a user, I want my personal data to be securely stored and encrypted so that my privacy is protected.
STATUS: Ready to Start
Onur
As a user, I want to be able to access the app at any time so that I can check my meal and exercise plans whenever I need.
STATUS: Ready to Start
Mehmet SM

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | User profile management | Not Started | Medium | 2027-06-17 | 2027-06-21 | 4 | Ensure changes are reflected immediately in app UI
Developer | User registration system | Ready to Start | High | 2027-06-17 | 2027-06-21 | 4 | Add optional 2FA to increase account security
Developer, Product Owner | Premium membership system | Not Started | Medium | 2027-06-20 | 2027-06-24 | 4 | Define premium tiers and features clearly
Developer | In-app purchase functionality | Not Started | Medium | 2027-06-20 | 2027-06-25 | 5 | Integrate with Apple Store and Google Play billing systems
9
BACKLOG
As a user, I want to view detailed exercise instructions (sets, reps, intensity, visuals) so that I can perform exercises correctly.
STATUS: Note Status Here
As a user, I want to create an account and log in/out using my email and password so that I can securely access the system.
STATUS: Ready to Start
As a user, I want to edit my profile information and profile picture so that I can personalize my account.
STATUS: Not Started
Kerem
As a user, I want my payments to be secure so that I can confidently purchase premium features or subscriptions without risk.
STATUS: Not Started
Salih
Yigit PO

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | AI infrastructure | Not Started | High | 2027-06-25 | 2027-06-29 | 4 | Ensure scalability and future integration with meal/exercise plan systems
Developer | Hugging Face API Integration | Not Started | High | 2027-06-29 | 2027-07-01 | 2 | Ensure secure API keys and rate limiting
Developer | Automated Scientific Analysis & API Integration | Not Started | Medium | 2027-07-01 | 2027-07-06 | 5 | Ensure API integration works for different paper formats
Developer | Customization and fine-tuning of the AI model | Not Started | Medium | 2027-07-01 | 2027-07-07 | 6 | Report Training metrics (loss, accuracy)
13
BACKLOG
As a user, I want to view scientific studies and their AI-generated summaries so that I can learn more about fitness and nutrition.
STATUS: Not Started
Mehmet SM
As a user, I want the AI to quickly analyze scientific papers and update recommendations so that I always get the most accurate and up-to-date guidance.
STATUS: Not Started
Onur

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | AI-based meal plan and exercise plan generation system | Not Started | Medium | 2027-07-07 | 2027-07-13 | 6 | Use user data and preferences to personalize recommendations
Developer | Design interactive home screen layouts | Not Started | Low | 2027-07-08 | 2027-07-11 | 3 | Test with different screen sizes and devices
Developer | Development of exercise plan components | Not Started | Low | 2027-07-13 | 2027-07-16 | 3 | Check that the user sees the same plan that the AI created
Developer | Development of push notification system | Not Started | Low | 2027-07-15 | 2027-07-17 | 2 | Allow users to customize notification times
11
BACKLOG
As a user, I want my exercise plan intensity to adjust based on my sleep and activity data so that it matches my physical condition.
STATUS: Not Started
As a user, I want AI-based recommendations for meals, supplements, and exercises so that I can optimize my performance.
STATUS: Not Started
As a user, I want to rate my daily meals and exercises so that the system can improve future recommendations.
STATUS: Not Started
As a user, I want to receive push notifications for exercise reminders and meal alerts so that I can stay on track with my daily plans.
STATUS: Not Started
Salih
Kerem
Utku
Yigit PO

## Sprint-5
SPRINT-5
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Scientific AI-generated summaries | Not Started | High | 2027-07-17 | 2027-07-20 | 3 | Ensure AI-generated summaries match original research findings
Developer, Product Owner | Leaderboard and ranking algorithm | Not Started | Medium | 2027-07-17 | 2027-07-21 | 4 | Handle edge cases appropriately
Developer | Creation of challenge system | Not Started | Medium | 2027-07-21 | 2027-07-25 | 4 | Notify users about challenge start/end
Developer | Integration with Apple Health and Google Fit | Not Started | High | 2027-07-22 | 2027-07-25 | 3 | Ensure compatibility with multiple devices
Developer, Product Owner | Development of admin panel | Not Started | Medium | 2027-07-25 | 2027-07-28 | 3 | Follow data protection regulations (KVKK) and best practices
12
BACKLOG
As a user, I want to view scientific studies and their AI-generated summaries so that I can learn more about fitness and nutrition.
STATUS: Not Started
As a user, I want to filter and sort the leaderboard so that I can analyze rankings easily.
STATUS: Not Started
As a user, I want the app to integrate with Apple Health and Google Fit so that my fitness and health data from other devices are automatically synchronized with the app.
STATUS: Not Started
As an admin, I want to manage users and content through an admin panel so that I can maintain the app, monitor activity, and ensure quality control.
STATUS: Not Started
Admin
Utku
Salih
Mehmet SM
As a user, I want to participate in weekly challenges and competitions so that I stay motivated and engaged with my exercise and meal plans.
STATUS: Not Started
Onur

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates (hidden)
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a user, I want to be able to access the app at any time so that I can check my meal and exercise plans whenever I need.
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here